## OutwardSF Ababil
| Product Name | Remittance | TC Start Date | 24th May, 2023 | Passed = 69
| Module Name | Ababil | TC End Date | 25th May, 2023 | Failed = 00
| Browser (tested) | Google Chrome, Microsoft Edge | Test Case Developed & Tested By | Shabbir Ajam Ulubbi | Observation = 02
| Developer Name | Pranab Datta | Test Reviewed By | Asrafun Nasa Anamika | Total = 71
TC_ID | Test Cases | Fields | Test Data | Expected Result | Actual Result | Bug Screenshot | Final Status | Type of Testing | Dev Status | QA Status
TC_001 | Check the field list as per Finacle | Outward | A/C: 1781360001572 | Field should be same as Finacle | Found as per Finacle |  | Passed | Positive Testing
TC_002 | Check the UI, spelling, color | Outward | A/C: 1781360001572 | UI should be same as Finacle | Found as per expectation |  | Passed | Positive Testing
TC_003 | Check without giving any data in the fields | Outward | N/A | Should show required msg for mandatory field | Showed |  | Passed | Negative Testing
TC_004 | Check the field with valid A/C & verify the balance auto populated or not | Outward->Charge Account Number | A/C: 1781500108282 | Should accept valid AC & show balance | Found proper |  | Passed | Positive Testing
TC_005 | Check the field with invalid A/C with space, extra digit, special character | Outward->Charge Account Number | A/C: 17815001082824, 1781500108282 4, 1781500108282@#$%, 17815001082824azs | Should show error pop-up msg | Found as per expectation |  | Passed | Negative Testing
TC_006 | Check drop-down data for Currency, Swift, Charges Outside BD, Purpose Code | Outward-> Currency, Swift, Charges Outside BD, Purpose Code | A/C: 1781360001572 | Drop-down data should be same as Finacle | Found proper |  | Passed | Positive Testing
TC_007 | Check with input multiple digit & verify "Amount in Word" field showed proper or not | Outward->Amount, Amount in Word | 12344567 | Should show successfully | Found as per expectation |  | Passed | Positive Testing
TC_008 | Check with input invalid digit & verify "Amount in Word" field showed proper or not | Outward->Amount, Amount in Word | 0012344500, 1332!@#$%^&, 1200dgh | Should show error msg below the field | Showed error msg |  | Passed | Negative Testing
TC_009 | Check by click "swift/code" field | Outward | N/A | Should visible swift bank name according to Swift | Showed error msg | Screen shot | Failed | Positive Testing |  | Passed
TC_010 | Verify when input swift/code, the swift bank name visible or not | Outward->SWIFT/Code | ZXZXZXZXXXX | Should show right swift bank name | Found as per expectation |  | Passed | Positive Testing
TC_011 | Verify when input invalid swift/code, the swift bank name visible or not | Outward->SWIFT/Code | ZXZXZXZ. ZXZXZXZABC | Should show error pop-up msg | Showed error msg |  | Passed | Negative Testing
TC_012 | Verify when input swift/code, the swift bank name visible or not | Outward->Intermediary SWIFT/Code | COBADEFFXXX | Should show right swift bank name | Found as per expectation |  | Passed | Positive Testing
TC_013 | Verify when input invalid swift/code, the swift bank name visible or not | Outward->Intermediary SWIFT/Code | COBADEF | Should show error pop-up msg | Showed error msg |  | Passed | Negative Testing
TC_014 | Check the text field with valid input | Outward->Beneficiary Name, Beneficiary Account, Beneficiary Address, Remarks1, Para, Chapter, Preferential Exchange Rate | Minal Roy, 1781580015897, Badda, test17, test90, 1009, 2, 1, 112 ​ | Should visible data properly | Found as per expectation |  | Passed | Positive Testing
TC_015 | Check the text field with invalid input | Outward->Beneficiary Name, Beneficiary Account, Beneficiary Address, Remarks1, Para, Chapter, Preferential Exchange Rate | Minal!@#454<?>"[;, 178800fgfd33#@, Badda-01, test17@!#$, 11234567890-9876543212345678 | Should show error msg for invalid input | Didn't show error msg for Beneficiary Account & Para/Chapter has no boundary value | Screen shot | Failed | Negative Testing |  | Passed
TC_016 | Check all the button work properly or not | Outward->Download TM File, Download Request Form, Save, Submit | N/A | Should works proper | Buttons are working perfectly |  | Passed | Positive Testing
TC_017 | Check "Download TM File", whether data visible properly or not | Outward->Download TM File button | N/A | Should show properly | Found error | Screen shot | Failed | Positive Testing |  | Passed
TC_018 | Check "Download Request Form", whether data visible properly or not | Outward->Download Request Form button | N/A | Should show properly | Found some mismatch | Screen shot | Failed | Positive Testing |  | Passed
TC_019 | Check pop-up msg when case forward from cs13 to bom13 | Outward | N/A | Should show success forward msg | Found proper |  | Passed | Positive Testing
TC_020 | Chcek the flow run properly or not from cs13 to bm13 | Outward | N/A | Should run properly | When add deferral, in bm13 showed nginx error | Screen shot | Failed | Positive Testing |  | Passed
TC_021 | Check the flow running or not from cs13->bom-13->maker20->checker20 | Outward | Fill up all valid data | Should run properly | Found successful |  | Passed | Positive Testing
TC_022 | In bom13, check all fields visible or not that fillup in cs13 | Outward->bom13 | N/A | Should visible properly | Found as per expectation |  | Passed | Positive Testing
TC_023 | In bom13, Check retun button working or not | Outward->bom13 | N/A | Should work properly | Found as per expectation |  | Passed | Positive Testing
TC_024 | Check the flow run from bom13 to maker20 or not | Outward->maker20 | N/A | Should run properly | Found as per expectation |  | Passed | Positive Testing
TC_025 | Verify all fields visible or not as per finacle | Outward->maker20 | N/A | Should visible properly every field | Found as per expectation |  | Passed | Positive Testing
TC_026 | Click "Submit" button without filing data | Outward->maker20 | N/A | Should show error msg for mandatory field | Found as per expectation |  | Passed | Negative Testing
TC_027 | Check all field with valid data | Outward->maker20 |  | Should accept all valid data | Accepts successfully |  | Passed
TC_028 | Check whether case run maker20 to checker20 properly or not | Outward->maker20 | N/A | Should run properly | Found as per expectation |  | Passed | Positive Testing
TC_029 | Check UI and field's visibility | Outward->checker20 | N/A | Should be perfect | Found perfect |  | Passed | Positive Testing
TC_030 | Check all buttons works properly or not | Outward->checker20 | N/A | Should be perfect | Found perfect |  | Passed | Positive Testing
TC_031 | Check transaction properly run or not | Outward->checker20 | N/A | Should proper transaction | Showed skipped ababil transaction | Screen shot | Failed | Positive Testing |  | Passed
TC_032 | Check "File Type" & "Account Source" drop down whether it shows correct data or not | Student File->Cs13 | N/A | Data should visible properly | Found as per expectation |  | Passed | Positive Testing
TC_033 | Check "Account Number" field by input valid A/C | Student File->Cs13->Open | 1781340004517 | Should accept | Accept successfully |  | Passed | Positive Testing
TC_034 | Check "Account Number" field by input invalid A/C | Student File->Cs13->Open | 17813400045 | Should show error msg | Showed error msg |  | Passed | Negative Testing
TC_035 | Check all fields visible proper & verify UI, Spelling | Student File->Cs13->Open | N/A | Fields & UI should be perfect | Found as per expectation |  | Passed | Positive Testing
TC_036 | Check all drop down data properly visible or not | Student File->Cs13->Open | N/A | Drop down data should visible properly | Found as per expectation |  | Passed | Positive Testing
TC_037 | Check all text field's able to write or not | Student File->Cs13->Open | 123, abc, @@#$^%$3. | Text field should be able to write | Found proper |  | Passed | Positive Testing
TC_038 | Chcek the flow run properly or not from cs13 to bm13 | Student File->Cs13->Open | N/A | Should run properly | When add deferral, in bm13 showed nginx error | Screen shot | Failed | Positive Testing |  | Passed
TC_039 | Check these fields with invalid input. Annual Expenses,Tuition Fee,Boarding/Lodging Fee,InsuranceTravel,Total Amount to be remitted in Advance,Details of Foreign Currency Purchase,Towards Tuition Fee,Towards Lodging Fee,Towards Travel,Towards Insurance,Towards Blocked Account | Student File->Cs13->Open | %00GHJJ@#$%^& | Shouldn't accept invalid input & should give error msg | Gave error msg |  | Passed | Negative Testing
TC_040 | Check "save" button & verify case went or not in "Pending Request" tab | Student File->Cs13->Open | N/A | Should run properly | Found perfect |  | Passed | Positive Testing
TC_041 | Check by click "Submit" button & check case run from cs13 to bom13 | Student File->Cs13->Open | N/A | Should run properly | Found as per expectation |  | Passed | Positive Testing
TC_042 | Check all fields visible proper & verify UI, Spelling | Student File->Bom13->Open | N/A | Ui should be perfect | Found as per expectation |  | Passed | Positive Testing
TC_043 | Check all fields read-only or editable | Student File->Bom13->Open | N/A | Should be read only mood | Found read only |  | Passed | Positive Testing
TC_044 | Check all buttons works proper or not-> Document 1, Preview Document, Approve, Return | Student File->Bom13->Open | N/A | Buttons should work properly | Found as per expectation |  | Passed | Positive Testing
TC_045 | Check all fields visible proper & verify UI, Spelling | Student File->maker20 ->Open | N/A | Should be proper | Found proper | Screen shot | Passed | Positive Testing
TC_046 | Check all buttons works proper or not-> Document 1, Preview Document, Preview Transaction, Return | Student File->maker20 ->Open | N/A | Should be proper | Found proper |  | Passed | Positive Testing
TC_047 | Check transaction page debit/credit calculation | Student File->maker20 ->Open | N/A | Should be appropriate | Found appropriate |  | Passed | Positive Testing
TC_048 | Check all fields visible proper or not | Student File->Checker20->Open | N/A | Should visible properly | Found proper |  | Passed | Positive Testing
TC_049 | Check transaction page debit/credit calculation | Student File->Checker20->Open | N/A | Should be appropriate | Found appropriate |  | Passed | Positive Testing
TC_050 | Check transaction happens properly or not | Student File->Checker20->Open | N/A | Should transaction properly | Transaction doesn't occur. showed permission msg | Screen shot | Failed | Positive Testing |  | Passed
TC_051 | Check all fields, drop down data, UI, spelling | Student File->Cs13->Update | A/C: 1781360001572 | Ui should be perfect | Found as per expectation |  | Passed | Positive Testing
TC_052 | Verify auto populated field visible properly or not | Student File->Cs13->Update | A/C: 1781360001572 | Should visible properly | Found proper |  | Passed | Positive Testing
TC_053 | Check editable field & all buttons works properly or not | Student File->Cs13->Update | A/C: 1781360001572 | Should works properly | Found proper |  | Passed | Positive Testing
TC_054 | Check case forward cs13 to bom13 & give forward msg or not | Student File->Cs13->Update | A/C: 1781360001572 | Should forward properly | Found proper |  | Passed | Positive Testing
TC_055 | Check all fields read only or editable | Student File->bom13->Update | A/C: 1781360001572 | Should read only mood | Found read only |  | Passed | Positive Testing
TC_056 | chcek all buttons works properly or not | Student File->bom13->Update | N/A | Should works properly | Found proper |  | Passed | Positive Testing
TC_057 | Check case move bom13 to maker20 or not | Student File->bom13->Update | N/A | Should flow properly | Found proper |  | Passed | Positive Testing
TC_058 | Check fields & buttons working or not | Student File->Maker20->Update | N/A | Should works properly | Found proper |  | Passed | Positive Testing
TC_059 | Check case run forward & give msg or not | Student File->Maker20->Update | N/A | Should flow properly | Found proper |  | Passed | Positive Testing
TC_060 | Check fields & buttons working or not | Student File->Maker20->Update | N/A | Should works properly | Found proper |  | Passed | Positive Testing
TC_061 | Check fields & buttons working or not | Student File->checker20->Update | N/A | Should works properly | Found proper |  | Passed | Positive Testing
TC_062 | Check case complete & give msg or not | Student File->checker20->Update | N/A | Should complete properly | Completed |  | Passed | Positive Testing
TC_063 | Check case update or not | Student File->cs13->Renew | A/C: 1781360001572 | Should Update properly | Updated properly |  | Passed | Positive Testing
TC_064 | Chcek cs->bom>maker>checker, whether all fields visible or not | Student File->cs13->Renew | N/A | Should visible properly | Found proper |  | Passed | Positive Testing
TC_065 | Chcek case successfully complete or not | Student File->cs13->Renew | N/A | Should complete properly | Completed |  | Passed | Positive Testing
TC_066 | Check visibility in auto populate field | Student File->cs13->Close | A/C: 1781360001572 | Should found perfect | "AD Branch" didn't gave data properly | Screen shot | Failed | Positive Testing |  | Passed
TC_067 | Check cs->bom>maker>checker, whether all fields visible or not | Student File->Close | N/A | Should visible properly | Found proper |  | Passed | Positive Testing
TC_068 | Check case successfully complete or not | Student File->Close | N/A | Should complete properly | Completed |  | Passed | Positive Testing
TC_069 | Check by update with same student file number | Student File->cs13->Update | 108-CSF-00050-23 | Should give error msg | Gave error msg |  | Passed | Positive Testing
TC_071 | Check all return button & verify case land corrcet tab or not | Case ID-1250 |  |  | bom13, maker20 theke case cs13 te return korle, cs13 theke approve korar por "forwarded to bom13" amn forward msg ashe na |  | Pending
| Check all return button & verify case land corrcet tab or not |  |  |  | bom theke return korle cs theke abr bom a jawar time forward msg not showing |  | Pending